## Read Me
Project Strategy TOR Dashboard - daily and monthly
Tracks delivery against what each project's Terms of Reference committed to. Log daily during the month; report monthly at governance.
What this workbook is for
A single pack the team can run at two speeds. Every metric answers one question: is this project still delivering what its Terms of Reference said it would, for the money and by the dates the TOR approved?
Two cadences, one dashboard
| Daily | Log progress each working day on 'Daily Log'. Use it to spot slippage inside the month, while there is still time to act. Set Dashboard C3 to Daily and put the date in C4.
| Monthly | One row per project per month on 'Monthly Log' - the governance and SteerCo record, and what the monthly trend charts keep. Set Dashboard C3 to Monthly and put the first day of the month in C4.
| How they join | Both logs hold the same cumulative-to-date figures, so the last daily row of a month IS that month's monthly row. The roll-up block on 'Daily Log' reads off any date so you can copy it straight into the Monthly Log - no double entry, no drift.
The daily routine - two minutes per project
| 1. Add today's rows | On 'Daily Log', copy yesterday's block down, change the date, and update anything that moved. Figures are CUMULATIVE TO DATE, not in-day.
| 2. Look at the Dashboard | Cadence Daily, today's date in C4. Anything Red or Amber is today's problem, not next month's.
The monthly cycle - five steps
| 1. Update registers | Add or update rows on 'Deliverables & RACI' and 'Risks & Issues' as things change.
| 2. Roll the month up | On 'Daily Log', put the month-end date in the roll-up block (cell R3). It shows each project's figures on that date. Copy them into a new month row on 'Monthly Log'. If the team does not log daily, just type the month's figures straight into 'Monthly Log'.
| 3. Copy the live counts | Copy Open Risks and High Risks from 'Risks & Issues', and RACI Gaps from 'Deliverables & RACI', into the month's row. Freezing them into the log is what gives the trend charts their history - the registers only ever show today.
| 4. Set cadence and month | On 'Dashboard', set C3 to Monthly and C4 to the first day of the month.
| 5. Review and present | Walk the Dashboard exception table, then 'Charts' for the trend. Red and Amber rows are the agenda.
Tab guide
| Read Me | This page.
| CEO Brief | Five decision-led bullets - money, benefits realisation, delivery, strategic pillar, scope drift - each carrying an ACT NOW / WATCH / OK flag and a Decision line. Every line is calculated from the Dashboard at the cadence and date set there, so it cannot be edited into a better story. This is what the file opens on.
| TOR Register | The baseline. One row per project holding what the signed TOR committed to: objective, scope boundaries, dates, approved budget, TARGET BENEFIT and the date benefits start, planned milestone and deliverable counts. Change this only through an approved change request.
| Daily Log | Day-by-day entry, one row per project per working day, cumulative to date. Also carries the month-end roll-up block.
| Monthly Log | One row per project per month, cumulative to date. The governance record and the source of the monthly trend charts.
| Deliverables & RACI | Deliverable-level register mapped back to TOR clauses, with Responsible / Accountable / Consulted / Informed. A blank Accountable is a governance gap and is counted for you.
| Risks & Issues | Risk and issue register with likelihood x impact scoring and live counts per project.
| Dashboard | Portfolio tiles and a per-project table, for whichever cadence C3 is set to.
| Charts | Monthly trend, per-project comparisons, and daily trend for the current month.
| Lists | Dropdown values. Extend here if the team uses different status wording.
How each metric is defined
| Scope adherence % | Deliverables accepted to date / deliverables due to date. Measures whether the TOR's promised outputs are actually landing and being accepted, not just started.
| Milestone hit rate % | Milestones achieved to date / milestones planned to date. Schedule health against the TOR baseline.
| Budget used % | Spend to date / TOR-approved budget. Over 100% means the project has spent past what the TOR authorised, regardless of how much work remains.
| Budget variance | TOR-approved budget less spend to date. Negative means overspent.
| Approved scope changes | Cumulative change requests approved. A rising count with a flat budget is the classic TOR drift signal - scope grew, funding did not.
| RACI gaps | Deliverables with no accountable owner named. Any number above zero is a governance finding, not a delivery one.
| Benefit realisation % | Benefit realised to date / target benefit, counting ONLY projects whose Benefits Start date has passed. A project that has not yet reached its benefits start is excluded, not counted as zero - otherwise every healthy early-stage project would look like a failure.
| Benefit gap | Budget used % minus benefit realisation %. Benefits lag spend by design, so this measures how far the two have drifted apart rather than treating any lag as a problem. Thresholds sit in Dashboard C12:C13.
| Strategic pillar | The portfolio grouped by the Strategic Pillar column on the TOR Register, so the brief can name the failing strategic bet rather than the failing project. Pick pillars from the dropdown so the grouping stays consistent; a pillar with nothing reporting is excluded from the weakest-pillar ranking rather than ranked at zero.
| Calculated RAG | Computed objectively from the thresholds in Dashboard C7:C11, so it cannot be talked up or down. Shown next to the PM's own RAG - a disagreement between the two is itself worth discussing.
Colour legend
| Blue text | A number or value you type in. Safe to edit.
| Yellow fill | Key input you are expected to set - cadence, reporting date, RAG thresholds, roll-up date.
| Black text | Formula calculated on that sheet. Do not overwrite.
| Green text | Value pulled from another sheet. Do not overwrite.
Capacity and assumptions
| Row capacity | TOR Register 40 projects; Daily Log 1500 rows; Monthly Log 300 rows; Deliverables and Risks 200 rows each. Formulas already cover every row in those ranges - just type into the next empty row.
| Date format | Daily Log takes the actual date. Monthly Log takes the FIRST DAY of the month (e.g. 2026-09-01) - the Dashboard matches on the exact date, so a mid-month date will not be picked up in Monthly cadence.
| Example data | The workbook ships with EXAMPLE data for five fictional projects: six months on 'Monthly Log' and the working days of the final month on 'Daily Log'. Names and figures are invented. Delete rows 4 and below on TOR Register, Daily Log, Monthly Log, Deliverables & RACI and Risks & Issues before real use.
| Currency | All money is in whole dollars. Change the number formats if the team reports in another unit.
| Source | Structure and metric definitions were specified for this request; there is no external data source behind the example figures.

## CEO Brief
CEO Brief - the five things to know
Written from the Dashboard, so it follows the cadence and reporting date set there. Every sentence below is a live formula, not typed text.
Calculation helpers - these feed the bullets; safe to ignore
| Cadence: | Monthly | [5 empty] | Project | Calc RAG | Over budget | Overspend $ | Has appr. CR | Hit rate | Exposure score | In benefit? | Target (in-ben) | Realised (in-ben)
| As at: | 2026-08-01 | Change the cadence or date on the Dashboard and this whole page rewrites itself. |  |  |  |  | Client Portal Rebuild | Amber | 0 | 0 | 1 | 77.78% | 33.8889 | 1 | 900000 | 95000
[8 empty] | Data Platform Migration | Green | 0 | 0 | 1 | 90% | 4 | 1 | 1400000 | 255000
|  | TOR budget | Spent to date | Budget used | Milestone hit rate | Scope adherence | Red / Amber / Green | Regulatory Reporting Uplift | Red | 1 | 11000 | 1 | 62.5% | 180 | 1 | 400000 | 42000
|  | 2545000 | 2092000 | 82.2% | 83.33% | 81.25% | 1 / 2 / 2 | Market Expansion - APAC | Green | 0 | 0 | 1 | 100% | 0 | 0 | 0 | 0
[8 empty] | Cost-to-Serve Optimisation | Amber | 0 | 0 | 1 | 85.71% | 10.7143 | 1 | 650000 | 205000
| The five things the CEO must know | [8 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
| Bottom line: 1 of 5 projects Red, 82% of the approved budget spent, 7 milestones and 9 deliverables outstanding against the TOR. 4 high-severity risks open. | [8 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
| ACT NOW | 1. $2,092,000 spent of $2,545,000 authorised (82%). 1 project over TOR budget by $11,000. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | The overspend is already committed - it is not a forecast. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Decision: fund the $11,000, cut scope on Regulatory Reporting Uplift, or re-baseline its TOR. Those are the only three options. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
| WATCH | 2. $597,000 of $3,350,000 promised benefits realised (18%), against 82% of budget spent. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Measured across the 4 of 5 reporting projects whose benefits have started - the rest are pre-benefit and excluded rather than counted as zero. Spend is ahead of value by 64 points. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Decision: check the benefit profile in each TOR. A lag this size is expected where benefits are back-loaded and is a problem where they are not - this workbook records when benefits start, not how they phase. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
| WATCH | 3. 83% of milestones hit, 81% of deliverables accepted. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Behind the TOR baseline by 7 milestones and 9 deliverables - against a milestone hit rate of 83% the month before. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Decision: ask how many of the 9 unaccepted deliverables are waiting on a sponsor signature rather than on the team. That split decides whether this is a delivery problem or a governance one. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
| ACT NOW | 4. Risk & Compliance is the weakest strategic pillar: 63% of its milestones hit, 103% of its budget used, across 1 project. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Its only project is Red, out of 5 pillars reporting. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Decision: fund, re-baseline or stop at pillar level. Reading the portfolio by strategic bet rather than by project is what shows whether the problem sits in one thesis or runs across all of them. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
| ACT NOW | 5. 10 change requests approved across 5 projects, against a TOR budget that has not moved. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Scope has grown; the approved funding has not. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Decision: ask finance whether the 10 approved changes were funded, and whether the promised benefit rose with the scope. If neither, the TOR is out of date on both counts. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
|  | Every line above - flags included - is calculated from the Dashboard at the cadence and date shown, so it is reproducible and cannot be edited into a better story. Flags: ACT NOW needs a decision this cycle, WATCH is deteriorating, OK needs nothing. Bullet 3 ranks projects by an exposure score (over-budget 100, each high-severity risk 15, each unowned deliverable 5, plus 40 x the share of milestones missed) - a heuristic for where to look first, not a formal risk measure. The working is in the helper block to the right. | [7 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[10 empty] | 0 | 0 | 0 |  | -1 | 0 | 0 | 0
[8 empty] | Projects over budget | 1
[8 empty] | Total overspend | 11000
[8 empty] | Projects with approved CRs | 5
[8 empty] | Worst project (by exposure) | Regulatory Reporting Uplift
[8 empty] | its milestone hit rate | 62.5%
[8 empty] | its budget used | 103.2%
[8 empty] | its high risks | 3
[8 empty] | its calculated RAG | Red
[8 empty] | Prior month | 2026-07-01
[8 empty] | Prior ms planned | 35
[8 empty] | Prior ms achieved | 29
[8 empty] | Prior hit rate | 82.86%
[8 empty] | Prior spend | 1728000
[8 empty] | Milestones behind | 7
[8 empty] | Deliverables not accepted | 9
[8 empty] | Approved CRs, total | 10
[8 empty] | Budget headroom | 453000
[8 empty] | Milestones planned, total | 42
[8 empty] | Milestones achieved, total | 35
[8 empty] | Deliverables due, total | 48
[8 empty] | Deliverables accepted, total | 39
[8 empty] | Largest overspender | Regulatory Reporting Uplift
[8 empty] | Hit rate vs prior month | 0.4762%
[8 empty] | Projects in benefit | 4
[8 empty] | Projects reporting | 5
[8 empty] | In-benefit target | 3350000
[8 empty] | In-benefit realised | 597000
[8 empty] | Benefit realisation % | 17.82%
[8 empty] | Benefit gap vs spend | 64.38%
[8 empty] | Weakest pillar | Risk & Compliance
[8 empty] | its hit rate | 62.5%
[8 empty] | its budget used | 103.2%
[8 empty] | its projects | 1
[8 empty] | its Red projects | 1
[8 empty] | Pillars reporting | 5
[8 empty] | Pillar | Projects | Budget | Spent | Ms planned | Ms achieved | Budget used | Hit rate | Red | Rank (low = worst)
[8 empty] | Digital Experience | 1 | 500000 | 412000 | 9 | 7 | 82.4% | 77.78% | 0 | 0.77778
[8 empty] | Data & Infrastructure | 1 | 820000 | 690000 | 10 | 9 | 84.15% | 90% | 0 | 0.9
[8 empty] | Risk & Compliance | 1 | 340000 | 351000 | 8 | 5 | 103.2% | 62.5% | 1 | 0.625
[8 empty] | Growth | 1 | 610000 | 415000 | 8 | 8 | 68.03% | 100% | 0 | 1
[8 empty] | Operating Efficiency | 1 | 275000 | 224000 | 7 | 6 | 81.45% | 85.71% | 0 | 0.85714

## TOR Register
TOR Register - the approved baseline
One row per project, straight from the signed Terms of Reference. Change only via an approved CR. EXAMPLE DATA - replace with the team's projects.
Project ID | Project Name | Strategic Pillar | Sponsor | Project Manager | TOR Approved | Planned Start | Planned End | TOR Approved Budget ($) | Target Benefit ($) | Benefits Start | Planned Milestones (total) | Planned Deliverables (total) | TOR Objective | Key In-Scope (per TOR) | Key Out-of-Scope (per TOR)
P-001 | Client Portal Rebuild | Digital Experience | A. Mensah | R. Patel | 2026-02-10 | 2026-03-01 | 2026-11-30 | 500000 | 900000 | 2026-07-01 | 9 | 12 | Replace the legacy client portal to cut self-service failure rate by half. | Portal UI, auth, self-service billing, migration of active accounts | Mobile app, partner API, archived account history
P-002 | Data Platform Migration | Data & Infrastructure | L. Njoku | S. Kowalski | 2026-02-03 | 2026-03-01 | 2027-01-29 | 820000 | 1400000 | 2026-06-01 | 12 | 15 | Move reporting workloads off the on-prem warehouse to the cloud platform. | ETL rebuild, warehouse cutover, BI re-point, decommission plan | ML feature store, real-time streaming, third-party data contracts
P-003 | Regulatory Reporting Uplift | Risk & Compliance | D. Ferreira | M. Haddad | 2026-02-17 | 2026-03-01 | 2026-10-30 | 340000 | 400000 | 2026-06-01 | 8 | 10 | Meet the new quarterly disclosure standard ahead of the Q1 2027 deadline. | Control redesign, evidence automation, submission templates, sign-off flow | Historic restatements, group consolidation changes
P-004 | Market Expansion - APAC | Growth | A. Mensah | T. Yamamoto | 2026-02-24 | 2026-03-01 | 2027-02-26 | 610000 | 2200000 | 2026-11-01 | 10 | 11 | Stand up sales and support operations in two APAC markets. | Entity setup, local hiring, pricing localisation, support coverage | Manufacturing footprint, local data centre, M&A options
P-005 | Cost-to-Serve Optimisation | Operating Efficiency | L. Njoku | C. Duarte | 2026-02-06 | 2026-03-01 | 2026-09-30 | 275000 | 650000 | 2026-05-01 | 7 | 9 | Reduce cost to serve per account by 15% without lowering CSAT. | Process redesign, tier-1 automation, vendor renegotiation | Headcount reduction, offshoring, product rationalisation

## Daily Log
Daily Log - day-by-day tracking inside the month
One row per project per working day. ALL FIGURES ARE CUMULATIVE TO DATE. EXAMPLE DATA - delete before real use. | [15 empty] | Month-end roll-up - set the date, copy the row into the Monthly Log
Date | Project ID | Milestones Planned to Date | Milestones Achieved to Date | Deliverables Due to Date | Deliverables Accepted to Date | Budget Spent to Date ($) | Benefit Realised to Date ($) | Change Requests Raised (cum.) | Change Requests Approved (cum.) | Open Risks (snapshot) | High Risks (snapshot) | RACI Gaps (snapshot) | PM RAG | Commentary | Match Key (auto) | Roll-up date: | 2026-08-31
2026-08-03 | P-001 | 8 | 7 | 9 | 8 | 354857 | 42619 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-03¦P-001 | Project | Ms Planned | Ms Achieved | Dl Due | Dl Accepted | Spend to Date ($) | Benefit ($) | CR Raised | CR Approved | Open Risks | High Risks | RACI Gaps | PM RAG
2026-08-03 | P-002 | 8 | 7 | 8 | 7 | 566190 | 155000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-03¦P-002 | P-001 | 9 | 7 | 11 | 9 | 412000 | 95000 | 3 | 2 | 3 | 1 | 2 | Amber
2026-08-03 | P-003 | 7 | 4 | 8 | 5 | 298619 | 30571 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-03¦P-003 | P-002 | 10 | 9 | 10 | 9 | 690000 | 255000 | 3 | 2 | 5 | 0 | 0 | Green
2026-08-03 | P-004 | 6 | 6 | 6 | 6 | 343571 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-03¦P-004 | P-003 | 8 | 5 | 10 | 6 | 351000 | 42000 | 5 | 4 | 9 | 3 | 4 | Red
2026-08-03 | P-005 | 6 | 5 | 7 | 6 | 182095 | 143095 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-03¦P-005 | P-004 | 8 | 8 | 8 | 8 | 415000 | 0 | 1 | 1 | 2 | 0 | 0 | Green
2026-08-04 | P-001 | 8 | 7 | 9 | 8 | 357714 | 45238 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-04¦P-001 | P-005 | 7 | 6 | 9 | 7 | 224000 | 205000 | 2 | 1 | 3 | 0 | 1 | Green
2026-08-04 | P-002 | 8 | 7 | 8 | 7 | 572381 | 160000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-04¦P-002
2026-08-04 | P-003 | 7 | 4 | 8 | 5 | 301238 | 31143 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-04¦P-003
2026-08-04 | P-004 | 6 | 6 | 6 | 6 | 347143 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-04¦P-004
2026-08-04 | P-005 | 6 | 5 | 7 | 6 | 184190 | 146190 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-04¦P-005
2026-08-05 | P-001 | 8 | 7 | 9 | 8 | 360571 | 47857 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-05¦P-001
2026-08-05 | P-002 | 8 | 7 | 8 | 7 | 578571 | 165000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-05¦P-002
2026-08-05 | P-003 | 7 | 4 | 8 | 5 | 303857 | 31714 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-05¦P-003
2026-08-05 | P-004 | 6 | 6 | 6 | 6 | 350714 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-05¦P-004
2026-08-05 | P-005 | 6 | 5 | 7 | 6 | 186286 | 149286 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-05¦P-005
2026-08-06 | P-001 | 8 | 7 | 9 | 8 | 363429 | 50476 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-06¦P-001
2026-08-06 | P-002 | 8 | 7 | 8 | 7 | 584762 | 170000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-06¦P-002
2026-08-06 | P-003 | 7 | 4 | 8 | 5 | 306476 | 32286 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-06¦P-003
2026-08-06 | P-004 | 6 | 6 | 6 | 6 | 354286 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-06¦P-004
2026-08-06 | P-005 | 6 | 5 | 7 | 6 | 188381 | 152381 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-06¦P-005
2026-08-07 | P-001 | 8 | 7 | 9 | 8 | 366286 | 53095 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-07¦P-001
2026-08-07 | P-002 | 8 | 7 | 8 | 7 | 590952 | 175000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-07¦P-002
2026-08-07 | P-003 | 7 | 4 | 8 | 5 | 309095 | 32857 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-07¦P-003
2026-08-07 | P-004 | 6 | 6 | 6 | 6 | 357857 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-07¦P-004
2026-08-07 | P-005 | 6 | 5 | 7 | 6 | 190476 | 155476 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-07¦P-005
2026-08-10 | P-001 | 8 | 7 | 10 | 8 | 369143 | 55714 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-10¦P-001
2026-08-10 | P-002 | 9 | 8 | 9 | 8 | 597143 | 180000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-10¦P-002
2026-08-10 | P-003 | 7 | 4 | 9 | 5 | 311714 | 33429 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-10¦P-003
2026-08-10 | P-004 | 7 | 7 | 7 | 7 | 361429 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-10¦P-004
2026-08-10 | P-005 | 6 | 5 | 8 | 6 | 192571 | 158571 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-10¦P-005
2026-08-11 | P-001 | 8 | 7 | 10 | 8 | 372000 | 58333 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-11¦P-001
2026-08-11 | P-002 | 9 | 8 | 9 | 8 | 603333 | 185000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-11¦P-002
2026-08-11 | P-003 | 7 | 4 | 9 | 5 | 314333 | 34000 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-11¦P-003
2026-08-11 | P-004 | 7 | 7 | 7 | 7 | 365000 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-11¦P-004
2026-08-11 | P-005 | 6 | 5 | 8 | 6 | 194667 | 161667 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-11¦P-005
2026-08-12 | P-001 | 8 | 7 | 10 | 8 | 374857 | 60952 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-12¦P-001
2026-08-12 | P-002 | 9 | 8 | 9 | 8 | 609524 | 190000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-12¦P-002
2026-08-12 | P-003 | 7 | 4 | 9 | 5 | 316952 | 34571 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-12¦P-003
2026-08-12 | P-004 | 7 | 7 | 7 | 7 | 368571 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-12¦P-004
2026-08-12 | P-005 | 6 | 5 | 8 | 6 | 196762 | 164762 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-12¦P-005
2026-08-13 | P-001 | 8 | 7 | 10 | 8 | 377714 | 63571 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-13¦P-001
2026-08-13 | P-002 | 9 | 8 | 9 | 8 | 615714 | 195000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-13¦P-002
2026-08-13 | P-003 | 7 | 4 | 9 | 5 | 319571 | 35143 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-13¦P-003
2026-08-13 | P-004 | 7 | 7 | 7 | 7 | 372143 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-13¦P-004
2026-08-13 | P-005 | 6 | 5 | 8 | 6 | 198857 | 167857 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-13¦P-005
2026-08-14 | P-001 | 8 | 7 | 10 | 8 | 380571 | 66190 | 3 | 2 | 4 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-14¦P-001
2026-08-14 | P-002 | 9 | 8 | 9 | 8 | 621905 | 200000 | 2 | 1 | 5 | 1 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-14¦P-002
2026-08-14 | P-003 | 7 | 4 | 9 | 5 | 322190 | 35714 | 4 | 3 | 9 | 3 | 3 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-14¦P-003
2026-08-14 | P-004 | 7 | 7 | 7 | 7 | 375714 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-14¦P-004
2026-08-14 | P-005 | 6 | 5 | 8 | 6 | 200952 | 170952 | 2 | 1 | 4 | 1 | 0 | Green | Tier-1 automation release in acceptance testing. | 2026-08-14¦P-005
2026-08-17 | P-001 | 9 | 7 | 10 | 9 | 383429 | 68810 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-17¦P-001
2026-08-17 | P-002 | 9 | 8 | 9 | 8 | 628095 | 205000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-17¦P-002
2026-08-17 | P-003 | 8 | 5 | 9 | 6 | 324810 | 36286 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-17¦P-003
2026-08-17 | P-004 | 7 | 7 | 7 | 7 | 379286 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-17¦P-004
2026-08-17 | P-005 | 7 | 6 | 8 | 7 | 203048 | 174048 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-17¦P-005
2026-08-18 | P-001 | 9 | 7 | 10 | 9 | 386286 | 71429 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-18¦P-001
2026-08-18 | P-002 | 9 | 8 | 9 | 8 | 634286 | 210000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-18¦P-002
2026-08-18 | P-003 | 8 | 5 | 9 | 6 | 327429 | 36857 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-18¦P-003
2026-08-18 | P-004 | 7 | 7 | 7 | 7 | 382857 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-18¦P-004
2026-08-18 | P-005 | 7 | 6 | 8 | 7 | 205143 | 177143 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-18¦P-005
2026-08-19 | P-001 | 9 | 7 | 10 | 9 | 389143 | 74048 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-19¦P-001
2026-08-19 | P-002 | 9 | 8 | 9 | 8 | 640476 | 215000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-19¦P-002
2026-08-19 | P-003 | 8 | 5 | 9 | 6 | 330048 | 37429 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-19¦P-003
2026-08-19 | P-004 | 7 | 7 | 7 | 7 | 386429 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-19¦P-004
2026-08-19 | P-005 | 7 | 6 | 8 | 7 | 207238 | 180238 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-19¦P-005
2026-08-20 | P-001 | 9 | 7 | 10 | 9 | 392000 | 76667 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-20¦P-001
2026-08-20 | P-002 | 9 | 8 | 9 | 8 | 646667 | 220000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-20¦P-002
2026-08-20 | P-003 | 8 | 5 | 9 | 6 | 332667 | 38000 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-20¦P-003
2026-08-20 | P-004 | 7 | 7 | 7 | 7 | 390000 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-20¦P-004
2026-08-20 | P-005 | 7 | 6 | 8 | 7 | 209333 | 183333 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-20¦P-005
2026-08-21 | P-001 | 9 | 7 | 10 | 9 | 394857 | 79286 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-21¦P-001
2026-08-21 | P-002 | 9 | 8 | 9 | 8 | 652857 | 225000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-21¦P-002
2026-08-21 | P-003 | 8 | 5 | 9 | 6 | 335286 | 38571 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-21¦P-003
2026-08-21 | P-004 | 7 | 7 | 7 | 7 | 393571 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-21¦P-004
2026-08-21 | P-005 | 7 | 6 | 8 | 7 | 211429 | 186429 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-21¦P-005
2026-08-24 | P-001 | 9 | 7 | 11 | 9 | 397714 | 81905 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-24¦P-001
2026-08-24 | P-002 | 10 | 9 | 10 | 9 | 659048 | 230000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-24¦P-002
2026-08-24 | P-003 | 8 | 5 | 10 | 6 | 337905 | 39143 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-24¦P-003
2026-08-24 | P-004 | 8 | 8 | 8 | 8 | 397143 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-24¦P-004
2026-08-24 | P-005 | 7 | 6 | 9 | 7 | 213524 | 189524 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-24¦P-005
2026-08-25 | P-001 | 9 | 7 | 11 | 9 | 400571 | 84524 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-25¦P-001
2026-08-25 | P-002 | 10 | 9 | 10 | 9 | 665238 | 235000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-25¦P-002
2026-08-25 | P-003 | 8 | 5 | 10 | 6 | 340524 | 39714 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-25¦P-003
2026-08-25 | P-004 | 8 | 8 | 8 | 8 | 400714 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-25¦P-004
2026-08-25 | P-005 | 7 | 6 | 9 | 7 | 215619 | 192619 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-25¦P-005
2026-08-26 | P-001 | 9 | 7 | 11 | 9 | 403429 | 87143 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-26¦P-001
2026-08-26 | P-002 | 10 | 9 | 10 | 9 | 671429 | 240000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-26¦P-002
2026-08-26 | P-003 | 8 | 5 | 10 | 6 | 343143 | 40286 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-26¦P-003
2026-08-26 | P-004 | 8 | 8 | 8 | 8 | 404286 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-26¦P-004
2026-08-26 | P-005 | 7 | 6 | 9 | 7 | 217714 | 195714 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-26¦P-005
2026-08-27 | P-001 | 9 | 7 | 11 | 9 | 406286 | 89762 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-27¦P-001
2026-08-27 | P-002 | 10 | 9 | 10 | 9 | 677619 | 245000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-27¦P-002
2026-08-27 | P-003 | 8 | 5 | 10 | 6 | 345762 | 40857 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-27¦P-003
2026-08-27 | P-004 | 8 | 8 | 8 | 8 | 407857 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-27¦P-004
2026-08-27 | P-005 | 7 | 6 | 9 | 7 | 219810 | 198810 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-27¦P-005
2026-08-28 | P-001 | 9 | 7 | 11 | 9 | 409143 | 92381 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan tasks progressing; auth cutover in test. | 2026-08-28¦P-001
2026-08-28 | P-002 | 10 | 9 | 10 | 9 | 683810 | 250000 | 3 | 2 | 5 | 0 | 0 | Green | Cutover runbook review and BI parity testing under way. | 2026-08-28¦P-002
2026-08-28 | P-003 | 8 | 5 | 10 | 6 | 348381 | 41429 | 5 | 4 | 9 | 3 | 4 | Red | Scope freeze in force pending the re-baseline paper. | 2026-08-28¦P-003
2026-08-28 | P-004 | 8 | 8 | 8 | 8 | 411429 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Second market onboarding on plan. | 2026-08-28¦P-004
2026-08-28 | P-005 | 7 | 6 | 9 | 7 | 221905 | 201905 | 2 | 1 | 3 | 0 | 1 | Green | Tier-1 automation release in acceptance testing. | 2026-08-28¦P-005
2026-08-31 | P-001 | 9 | 7 | 11 | 9 | 412000 | 95000 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan agreed; hit rate improving but still behind TOR. | 2026-08-31¦P-001
2026-08-31 | P-002 | 10 | 9 | 10 | 9 | 690000 | 255000 | 3 | 2 | 5 | 0 | 0 | Green | Tracking to TOR; decommission CR approved. | 2026-08-31¦P-002
2026-08-31 | P-003 | 8 | 5 | 10 | 6 | 351000 | 42000 | 5 | 4 | 9 | 3 | 4 | Red | Overspent vs TOR budget. Re-baseline decision needed at SteerCo. | 2026-08-31¦P-003
2026-08-31 | P-004 | 8 | 8 | 8 | 8 | 415000 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Both markets on track to TOR end date. | 2026-08-31¦P-004
2026-08-31 | P-005 | 7 | 6 | 9 | 7 | 224000 | 205000 | 2 | 1 | 3 | 0 | 1 | Green | Two deliverables pending acceptance, otherwise on plan. | 2026-08-31¦P-005

## Monthly Log
Monthly Log - the governance record
One row per project per month. ALL FIGURES ARE CUMULATIVE TO DATE. Enter the first day of the month. EXAMPLE DATA - delete before real use.
Month (1st of month) | Project ID | Milestones Planned to Date | Milestones Achieved to Date | Deliverables Due to Date | Deliverables Accepted to Date | Budget Spent to Date ($) | Benefit Realised to Date ($) | Change Requests Raised (cum.) | Change Requests Approved (cum.) | Open Risks (snapshot) | High Risks (snapshot) | RACI Gaps (snapshot) | PM RAG | Commentary | Match Key (auto)
2026-03-01 | P-001 | 2 | 2 | 2 | 2 | 72000 | 0 | 0 | 0 | 3 | 0 | 1 | Green | Kick-off complete, TOR baselined. | 2026-03¦P-001
2026-03-01 | P-002 | 1 | 1 | 1 | 1 | 95000 | 0 | 1 | 0 | 5 | 1 | 2 | Amber | Two RACI gaps flagged at TOR review. | 2026-03¦P-002
2026-03-01 | P-003 | 2 | 2 | 2 | 2 | 58000 | 0 | 0 | 0 | 4 | 1 | 0 | Green | Baselined against draft standard. | 2026-03¦P-003
2026-03-01 | P-004 | 1 | 1 | 1 | 1 | 60000 | 0 | 0 | 0 | 2 | 0 | 0 | Green | Entity setup started on schedule. | 2026-03¦P-004
2026-03-01 | P-005 | 1 | 1 | 1 | 1 | 30000 | 0 | 0 | 0 | 3 | 0 | 1 | Green | Baseline agreed with operations. | 2026-03¦P-005
2026-04-01 | P-001 | 3 | 3 | 4 | 4 | 140000 | 0 | 1 | 1 | 4 | 1 | 1 | Green | Auth vendor confirmed; first CR raised on billing scope. | 2026-04¦P-001
2026-04-01 | P-002 | 2 | 2 | 3 | 3 | 190000 | 0 | 1 | 1 | 5 | 1 | 1 | Amber | Ownership resolved for ETL workstream. | 2026-04¦P-002
2026-04-01 | P-003 | 3 | 3 | 3 | 3 | 112000 | 0 | 0 | 0 | 5 | 1 | 1 | Amber | Regulator clarification pending, first slip. | 2026-04¦P-003
2026-04-01 | P-004 | 2 | 2 | 2 | 2 | 125000 | 0 | 0 | 0 | 2 | 0 | 0 | Green | Local counsel engaged, no issues. | 2026-04¦P-004
2026-04-01 | P-005 | 2 | 2 | 2 | 2 | 62000 | 0 | 1 | 0 | 3 | 0 | 1 | Green | Vendor renegotiation opened. | 2026-04¦P-005
2026-05-01 | P-001 | 5 | 4 | 5 | 4 | 205000 | 0 | 1 | 1 | 4 | 1 | 0 | Amber | Design sign-off slipped 2 weeks; one milestone missed. | 2026-05¦P-001
2026-05-01 | P-002 | 4 | 4 | 4 | 4 | 300000 | 0 | 2 | 1 | 6 | 2 | 1 | Amber | Cutover risk raised to high pending capacity test. | 2026-05¦P-002
2026-05-01 | P-003 | 4 | 3 | 4 | 3 | 168000 | 0 | 1 | 1 | 7 | 2 | 2 | Amber | Scope grew: evidence automation added by CR. | 2026-05¦P-003
2026-05-01 | P-004 | 3 | 3 | 3 | 3 | 190000 | 0 | 0 | 0 | 3 | 0 | 0 | Green | Hiring pipeline ahead of plan. | 2026-05¦P-004
2026-05-01 | P-005 | 3 | 3 | 3 | 3 | 95000 | 20000 | 1 | 0 | 3 | 1 | 1 | Amber | Automation vendor risk raised to high. | 2026-05¦P-005
2026-06-01 | P-001 | 6 | 5 | 7 | 6 | 286000 | 0 | 2 | 1 | 5 | 1 | 0 | Amber | Migration dry-run failed once, retest scheduled. | 2026-06¦P-001
2026-06-01 | P-002 | 6 | 6 | 6 | 5 | 430000 | 60000 | 2 | 1 | 6 | 1 | 0 | Green | Capacity test passed; back on plan. | 2026-06¦P-002
2026-06-01 | P-003 | 5 | 3 | 6 | 4 | 232000 | 15000 | 3 | 2 | 8 | 3 | 3 | Red | Budget forecast breached; escalated to sponsor. | 2026-06¦P-003
2026-06-01 | P-004 | 5 | 5 | 4 | 4 | 268000 | 0 | 1 | 1 | 3 | 0 | 0 | Green | Pricing CR approved, budget unchanged. | 2026-06¦P-004
2026-06-01 | P-005 | 4 | 4 | 5 | 4 | 138000 | 75000 | 1 | 0 | 4 | 1 | 0 | Amber | Mitigation in place, second vendor shortlisted. | 2026-06¦P-005
2026-07-01 | P-001 | 8 | 7 | 9 | 8 | 352000 | 40000 | 3 | 2 | 4 | 1 | 2 | Amber | Two deliverables awaiting sponsor acceptance. | 2026-07¦P-001
2026-07-01 | P-002 | 8 | 7 | 8 | 7 | 560000 | 150000 | 2 | 1 | 5 | 1 | 0 | Green | One milestone slipped into next month, no scope impact. | 2026-07¦P-002
2026-07-01 | P-003 | 7 | 4 | 8 | 5 | 296000 | 30000 | 4 | 3 | 9 | 3 | 3 | Red | Four unowned deliverables, accountability unresolved. | 2026-07¦P-003
2026-07-01 | P-004 | 6 | 6 | 6 | 6 | 340000 | 0 | 1 | 1 | 2 | 0 | 0 | Green | First market live. | 2026-07¦P-004
2026-07-01 | P-005 | 6 | 5 | 7 | 6 | 180000 | 140000 | 2 | 1 | 4 | 1 | 0 | Green | Vendor risk closed; CR approved for extra automation. | 2026-07¦P-005
2026-08-01 | P-001 | 9 | 7 | 11 | 9 | 412000 | 95000 | 3 | 2 | 3 | 1 | 2 | Amber | Recovery plan agreed; hit rate improving but still behind TOR. | 2026-08¦P-001
2026-08-01 | P-002 | 10 | 9 | 10 | 9 | 690000 | 255000 | 3 | 2 | 5 | 0 | 0 | Green | Tracking to TOR; decommission CR approved. | 2026-08¦P-002
2026-08-01 | P-003 | 8 | 5 | 10 | 6 | 351000 | 42000 | 5 | 4 | 9 | 3 | 4 | Red | Overspent vs TOR budget. Re-baseline decision needed at SteerCo. | 2026-08¦P-003
2026-08-01 | P-004 | 8 | 8 | 8 | 8 | 415000 | 0 | 1 | 1 | 2 | 0 | 0 | Green | Both markets on track to TOR end date. | 2026-08¦P-004
2026-08-01 | P-005 | 7 | 6 | 9 | 7 | 224000 | 205000 | 2 | 1 | 3 | 0 | 1 | Green | Two deliverables pending acceptance, otherwise on plan. | 2026-08¦P-005

## Deliverables & RACI
Deliverables & RACI - TOR outputs and who owns them
A blank Accountable is a governance gap and is counted automatically. EXAMPLE DATA - delete before real use. | [9 empty] | Live register counts
Deliverable ID | Project ID | Deliverable (per TOR) | TOR Clause Ref | Responsible | Accountable | Consulted | Informed | Due Date | Status | Project | In Register | Accepted | RACI Gaps -> copy to log
D-001 | P-001 | Portal design system sign-off | TOR 4.1 | R. Patel | A. Mensah | Design guild | Steering group | 2026-04-30 | Accepted | P-001 | 4 | 1 | 2
D-002 | P-001 | Authentication service cutover | TOR 4.2 | K. Osei | R. Patel | Security | Service desk | 2026-07-31 | Submitted | P-002 | 3 | 1 | 0
D-003 | P-001 | Self-service billing module | TOR 4.3 | K. Osei |  | Finance ops | Client services | 2026-09-30 | In Progress | P-003 | 5 | 1 | 4
D-004 | P-001 | Active account migration | TOR 4.4 | J. Silva |  | Data team | Steering group | 2026-10-30 | Not Started | P-004 | 3 | 2 | 0
D-005 | P-002 | ETL rebuild - phase 1 | TOR 3.1 | S. Kowalski | L. Njoku | Platform | BI users | 2026-05-29 | Accepted | P-005 | 3 | 1 | 1
D-006 | P-002 | Warehouse cutover runbook | TOR 3.2 | N. Abebe | S. Kowalski | Ops | All staff | 2026-08-31 | Submitted
D-007 | P-002 | BI re-point and validation | TOR 3.3 | N. Abebe | S. Kowalski | Finance | BI users | 2026-10-30 | In Progress | Only the RACI gap count is copied into the logs. This register holds the major TOR deliverables and their ownership; the logs' 'due / accepted' counts come from the full delivery plan, so they are normally larger.
D-008 | P-003 | Control redesign pack | TOR 2.1 | M. Haddad | D. Ferreira | Internal audit | Board | 2026-05-29 | Accepted
D-009 | P-003 | Evidence automation build | TOR 2.4 (CR-03) | P. Lindqvist |  | Compliance | Board | 2026-08-31 | In Progress
D-010 | P-003 | Submission template set | TOR 2.2 | P. Lindqvist |  | Regulator liaison | Board | 2026-09-30 | Not Started
D-011 | P-003 | Sign-off workflow | TOR 2.3 | M. Haddad |  | Legal | Board | 2026-10-30 | Not Started
D-012 | P-003 | Historic restatement review | TOR 2.5 (CR-04) | M. Haddad |  | Finance | Board | 2026-10-30 | Not Started
D-013 | P-004 | APAC entity registration | TOR 5.1 | T. Yamamoto | A. Mensah | Legal | Exec | 2026-05-29 | Accepted
D-014 | P-004 | Localised pricing model | TOR 5.2 | H. Tran | T. Yamamoto | Finance | Sales | 2026-07-31 | Accepted
D-015 | P-004 | Regional support coverage | TOR 5.3 | H. Tran | T. Yamamoto | Support | Clients | 2026-11-30 | In Progress
D-016 | P-005 | Process redesign blueprint | TOR 6.1 | C. Duarte | L. Njoku | Ops leads | Exec | 2026-05-29 | Accepted
D-017 | P-005 | Tier-1 automation release | TOR 6.2 | E. Boateng | C. Duarte | Service desk | Ops | 2026-08-31 | Submitted
D-018 | P-005 | Vendor contract renegotiation | TOR 6.3 | E. Boateng |  | Procurement | Finance | 2026-09-30 | In Progress

## Risks & Issues
Risks & Issues register
Score = likelihood x impact. Severity and the live counts are calculated. EXAMPLE DATA - delete before real use. | [12 empty] | Live counts - copy into the logs
ID | Project ID | Type | Description | Likelihood (1-5) | Impact (1-5) | Score | Severity | Owner | Mitigation / Action | Status | Raised | Target Close | Project | Open Risks -> copy to log | High Risks -> copy to log
R-001 | P-001 | Risk | Auth vendor cannot meet the agreed cutover window | 3 | 4 | 12 | Medium | R. Patel | Parallel-run window booked; fallback to extended legacy support | Mitigating | 2026-04-14 | 2026-09-30 | P-001 | 3 | 1
R-002 | P-001 | Issue | Design sign-off slipped two weeks against the TOR schedule | 5 | 3 | 15 | High | R. Patel | Recovery plan agreed with sponsor; two milestones re-sequenced | Open | 2026-05-12 | 2026-09-15 | P-002 | 5 | 0
R-003 | P-001 | Risk | Billing scope creep beyond TOR 4.3 without an approved CR | 3 | 3 | 9 | Medium | A. Mensah | CR-02 tabled at SteerCo for decision | Open | 2026-07-08 | 2026-09-30 | P-003 | 9 | 3
R-004 | P-002 | Risk | Cutover exceeds the agreed maintenance window | 2 | 5 | 10 | Medium | S. Kowalski | Capacity test passed; rehearsal booked for October | Mitigating | 2026-05-06 | 2026-10-15 | P-004 | 2 | 0
R-005 | P-002 | Risk | Legacy warehouse licence renews before decommission | 3 | 3 | 9 | Medium | L. Njoku | Decommission CR approved; renewal deferred to monthly terms | Closed | 2026-04-02 | 2026-08-01 | P-005 | 3 | 0
R-006 | P-003 | Issue | Forecast spend exceeds the TOR-approved budget | 5 | 5 | 25 | High | D. Ferreira | Re-baseline paper going to SteerCo; scope freeze in force | Open | 2026-06-10 | 2026-09-15
R-007 | P-003 | Issue | Four deliverables have no accountable owner | 5 | 4 | 20 | High | D. Ferreira | Accountability workshop scheduled with the sponsor | Open | 2026-07-03 | 2026-09-12
R-008 | P-003 | Risk | Regulator clarification may reopen the control design | 3 | 4 | 12 | Medium | M. Haddad | Formal query submitted; contingency in the plan | Open | 2026-04-21 | 2026-10-30
R-009 | P-003 | Risk | Scope added by CR-03/CR-04 not funded in the TOR | 4 | 4 | 16 | High | D. Ferreira | Funding request bundled with the re-baseline paper | Open | 2026-06-25 | 2026-09-15
R-010 | P-004 | Risk | Local hiring lead times slip in the second market | 2 | 3 | 6 | Low | T. Yamamoto | Agency retained; pipeline running two candidates deep | Mitigating | 2026-05-18 | 2026-11-30
R-011 | P-004 | Risk | Currency movement erodes the localised pricing margin | 2 | 3 | 6 | Low | H. Tran | Quarterly price review clause added to contracts | Open | 2026-07-15 | 2026-12-18
R-012 | P-005 | Risk | Automation vendor stability after the funding round | 2 | 4 | 8 | Medium | C. Duarte | Second vendor shortlisted; source code escrow agreed | Closed | 2026-05-20 | 2026-08-14
R-013 | P-005 | Risk | Benefit realisation depends on a CSAT floor being held | 3 | 3 | 9 | Medium | C. Duarte | CSAT tracked weekly; rollback trigger defined | Mitigating | 2026-06-30 | 2026-09-30
R-014 | P-002 | Risk | Source system owners slow to sign off data contracts | 3 | 3 | 9 | Medium | S. Kowalski | Contract templates pre-agreed; weekly chase in the workstream call | Open | 2026-06-08 | 2026-10-30
R-015 | P-002 | Risk | BI report parity testing may run past the agreed window | 3 | 4 | 12 | Medium | N. Abebe | Parity suite automated; top 40 reports prioritised | Mitigating | 2026-07-01 | 2026-11-27
R-016 | P-002 | Issue | Two ETL jobs exceed the nightly batch window | 4 | 3 | 12 | Medium | N. Abebe | Partitioning rework in flight; interim staggered schedule | Open | 2026-07-22 | 2026-09-30
R-017 | P-002 | Risk | Cloud run-rate tracking above the TOR estimate | 2 | 4 | 8 | Medium | S. Kowalski | Reserved capacity purchased; monthly cost review added | Mitigating | 2026-08-05 | 2026-12-18
R-018 | P-003 | Risk | Evidence automation depends on a single contractor | 3 | 4 | 12 | Medium | M. Haddad | Knowledge transfer sessions booked; handover pack required | Mitigating | 2026-06-17 | 2026-10-15
R-019 | P-003 | Risk | Template changes require a second legal review | 3 | 3 | 9 | Medium | M. Haddad | Legal slot pre-booked for the October cycle | Open | 2026-07-09 | 2026-10-16
R-020 | P-003 | Issue | Control testing environment unavailable for two weeks in September | 4 | 3 | 12 | Medium | P. Lindqvist | Testing re-sequenced; shared environment booked as fallback | Open | 2026-08-12 | 2026-09-26
R-021 | P-003 | Risk | Sign-off workflow tooling licence not yet procured | 3 | 3 | 9 | Medium | D. Ferreira | Procurement raised; manual workflow as interim | Open | 2026-08-03 | 2026-09-30
R-022 | P-003 | Risk | Reporting calendar clashes with year-end close | 2 | 4 | 8 | Medium | D. Ferreira | Dates agreed with finance; submission moved one week earlier | Mitigating | 2026-08-19 | 2026-11-30
R-023 | P-005 | Risk | Process redesign adoption varies by region | 3 | 3 | 9 | Medium | C. Duarte | Regional champions appointed; adoption tracked weekly | Open | 2026-07-14 | 2026-09-30
R-024 | P-005 | Risk | Benefit baseline disputed by finance | 2 | 4 | 8 | Medium | C. Duarte | Baseline restated with finance and re-signed by the sponsor | Mitigating | 2026-08-07 | 2026-09-26

## Dashboard
Dashboard - delivery against TOR
Set the cadence in C3 and the reporting date in C4. Everything below recalculates. Red and Amber rows are the agenda.
| Cadence: | Monthly | <- Daily reads the Daily Log; Monthly reads the Monthly Log
| Reporting date: | 2026-08-01 | <- Daily: the actual date. Monthly: the FIRST DAY of the month, e.g. 2026-09-01
| RAG thresholds (edit to match the team's tolerance) |  |  |  |  | Portfolio for the selected cadence and date
| Milestone hit rate - Amber below | 90% | Below this, schedule is off the TOR baseline enough to flag. |  |  | Projects reporting |  | TOR budget ($) |  | Spent to date ($) |  | Budget used % |  | Milestone hit rate % |  | Scope adherence %
| Milestone hit rate - Red below | 75% | Below this, the TOR schedule is not credible without a re-baseline. |  |  | 5 |  | 2545000 |  | 2092000 |  | 82.2% |  | 83.33% |  | 81.25%
| Budget used - Amber above | 95% | Approaching the TOR-authorised budget.
| Budget used - Red above | 100% | Spent past what the TOR authorised. |  |  | Open risks |  | High risks |  | RACI gaps |  | Projects Red |  | Projects Amber |  | Projects Green
| High risks - Red at or above | 2 | This many unclosed high-severity risks forces a Red. |  |  | 22 |  | 4 |  | 7 |  | 1 |  | 2 |  | 2
| Benefit gap - Amber above | 50% | Budget used % minus benefit realised %. Benefits lag spend by design; this is how big a lag is worth raising.
| Benefit gap - Red above | 70% | A gap this wide means spend and value have decoupled.
Project detail for the selected cadence and date
Project ID | Project Name | PM | TOR Budget ($) | Spent to Date ($) | Budget Used % | Budget Variance ($) | Milestones Planned | Milestones Achieved | Milestone Hit Rate % | Deliverables Due | Deliverables Accepted | Scope Adherence % | Approved Scope Changes | Open Risks | High Risks | RACI Gaps | PM RAG | Calculated RAG | PM Commentary | Strategic Pillar | Target Benefit ($) | Benefit Realised ($) | Benefit Realised %
P-001 | Client Portal Rebuild | R. Patel | 500000 | 412000 | 82.4% | 88000 | 9 | 7 | 77.78% | 11 | 9 | 81.82% | 2 | 3 | 1 | 2 | Amber | Amber | Recovery plan agreed; hit rate improving but still behind TOR. | Digital Experience | 900000 | 95000 | 10.56%
P-002 | Data Platform Migration | S. Kowalski | 820000 | 690000 | 84.15% | 130000 | 10 | 9 | 90% | 10 | 9 | 90% | 2 | 5 | 0 | 0 | Green | Green | Tracking to TOR; decommission CR approved. | Data & Infrastructure | 1400000 | 255000 | 18.21%
P-003 | Regulatory Reporting Uplift | M. Haddad | 340000 | 351000 | 103.2% | -11000 | 8 | 5 | 62.5% | 10 | 6 | 60% | 4 | 9 | 3 | 4 | Red | Red | Overspent vs TOR budget. Re-baseline decision needed at SteerCo. | Risk & Compliance | 400000 | 42000 | 10.5%
P-004 | Market Expansion - APAC | T. Yamamoto | 610000 | 415000 | 68.03% | 195000 | 8 | 8 | 100% | 8 | 8 | 100% | 1 | 2 | 0 | 0 | Green | Green | Both markets on track to TOR end date. | Growth | 2200000 | 0
P-005 | Cost-to-Serve Optimisation | C. Duarte | 275000 | 224000 | 81.45% | 51000 | 7 | 6 | 85.71% | 9 | 7 | 77.78% | 1 | 3 | 0 | 1 | Green | Amber | Two deliverables pending acceptance, otherwise on plan. | Operating Efficiency | 650000 | 205000 | 31.54%
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
|  |  |  | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | [5 empty] | 0
Notes and assumptions
- Cadence C3 chooses the source: Daily reads 'Daily Log' and matches the exact date in C4; Monthly reads 'Monthly Log' and matches the first day of the month in C4.
- Both logs hold cumulative-to-date figures, so every metric here is 'position as at the reporting date', not activity within that day or month.
- Because both logs are cumulative, the last daily row of a month equals that month's monthly row - the two cadences agree at month end by construction.
- Scope adherence = deliverables accepted / deliverables due to date. Approved scope changes are shown separately: a rising CR count against a flat TOR budget is scope drift, even when the adherence percentage looks healthy.
- Calculated RAG is derived only from the thresholds in C7:C11 and the raw counts, so it is reproducible. Where it disagrees with the PM RAG, the difference is the discussion.
- 'Not started' appears when a project has no milestones due, no deliverables due and no spend as at the reporting date.
- Rows are driven by the TOR Register: add a project there and it appears here automatically, up to the register's capacity.
- Open risks counts anything not Closed (Open + Mitigating) on the Risks & Issues register at the point the snapshot was taken.

## Charts
Trend and comparison charts
Monthly trend and per-project comparison at the top; daily trend for the current month below. Add a row to a block and its chart extends.
Month | Milestones Planned | Milestones Achieved | Milestone Hit Rate % | Deliverables Due | Deliverables Accepted | Scope Adherence % | Budget Spent to Date ($) | Open Risks | High Risks | RACI Gaps | Benefit Realised to Date ($)
2026-03-01 | 7 | 7 | 100% | 7 | 7 | 100% | 315000 | 17 | 2 | 4 | 0
2026-04-01 | 12 | 12 | 100% | 14 | 14 | 100% | 629000 | 19 | 3 | 4 | 0
2026-05-01 | 19 | 17 | 89.47% | 19 | 17 | 89.47% | 958000 | 23 | 6 | 4 | 20000
2026-06-01 | 26 | 23 | 88.46% | 28 | 23 | 82.14% | 1354000 | 26 | 6 | 3 | 150000
2026-07-01 | 35 | 29 | 82.86% | 38 | 32 | 84.21% | 1728000 | 24 | 6 | 5 | 360000
2026-08-01 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2092000 | 22 | 4 | 7 | 597000
Per-project comparison - follows the cadence and date set on the Dashboard (covers the projects present when this workbook was generated; re-run the generator after adding projects)
Project | TOR Budget ($) | Spent to Date ($) | Milestone Hit Rate % | Scope Adherence %
Client Portal Rebuild | 500000 | 412000 | 77.78% | 81.82%
Data Platform Migration | 820000 | 690000 | 90% | 90%
Regulatory Reporting Uplift | 340000 | 351000 | 62.5% | 60%
Market Expansion - APAC | 610000 | 415000 | 100% | 100%
Cost-to-Serve Optimisation | 275000 | 224000 | 85.71% | 77.78%
Daily trend - portfolio position by day, straight from the Daily Log
Date | Milestones Planned | Milestones Achieved | Milestone Hit Rate % | Deliverables Due | Deliverables Accepted | Scope Adherence % | Budget Spent to Date ($) | Open Risks | High Risks | RACI Gaps
2026-08-03 | 35 | 29 | 82.86% | 38 | 32 | 84.21% | 1745332 | 24 | 6 | 5
2026-08-04 | 35 | 29 | 82.86% | 38 | 32 | 84.21% | 1762666 | 24 | 6 | 5
2026-08-05 | 35 | 29 | 82.86% | 38 | 32 | 84.21% | 1779999 | 24 | 6 | 5
2026-08-06 | 35 | 29 | 82.86% | 38 | 32 | 84.21% | 1797334 | 24 | 6 | 5
2026-08-07 | 35 | 29 | 82.86% | 38 | 32 | 84.21% | 1814666 | 24 | 6 | 5
2026-08-10 | 37 | 31 | 83.78% | 43 | 34 | 79.07% | 1832000 | 24 | 6 | 5
2026-08-11 | 37 | 31 | 83.78% | 43 | 34 | 79.07% | 1849333 | 24 | 6 | 5
2026-08-12 | 37 | 31 | 83.78% | 43 | 34 | 79.07% | 1866666 | 24 | 6 | 5
2026-08-13 | 37 | 31 | 83.78% | 43 | 34 | 79.07% | 1883999 | 24 | 6 | 5
2026-08-14 | 37 | 31 | 83.78% | 43 | 34 | 79.07% | 1901332 | 24 | 6 | 5
2026-08-17 | 40 | 33 | 82.5% | 43 | 37 | 86.05% | 1918668 | 22 | 4 | 7
2026-08-18 | 40 | 33 | 82.5% | 43 | 37 | 86.05% | 1936001 | 22 | 4 | 7
2026-08-19 | 40 | 33 | 82.5% | 43 | 37 | 86.05% | 1953334 | 22 | 4 | 7
2026-08-20 | 40 | 33 | 82.5% | 43 | 37 | 86.05% | 1970667 | 22 | 4 | 7
2026-08-21 | 40 | 33 | 82.5% | 43 | 37 | 86.05% | 1988000 | 22 | 4 | 7
2026-08-24 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2005334 | 22 | 4 | 7
2026-08-25 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2022666 | 22 | 4 | 7
2026-08-26 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2040001 | 22 | 4 | 7
2026-08-27 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2057334 | 22 | 4 | 7
2026-08-28 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2074668 | 22 | 4 | 7
2026-08-31 | 42 | 35 | 83.33% | 48 | 39 | 81.25% | 2092000 | 22 | 4 | 7

## Lists
Dropdown lists
Extend a column and the matching dropdown picks it up. Keep RAG wording as Green / Amber / Red and cadence as Daily / Monthly - the formulas match on them.
RAG | Deliverable Status | Risk/Issue Status | Type | Score 1-5 | Cadence | Strategic Pillar
Green | Not Started | Open | Risk | 1 | Daily | Digital Experience
Amber | In Progress | Mitigating | Issue | 2 | Monthly | Data & Infrastructure
Red | Submitted | Closed |  | 3 |  | Risk & Compliance
| Accepted |  |  | 4 |  | Growth
| Descoped |  |  | 5 |  | Operating Efficiency